## Roadmap
Six-week roadmap: 19 Oct to 29 Nov 2026 (conference 2-4 Dec 2026, PJTAU Hyderabad)
Yellow cells are for you to update (status). Dates are planned targets from the roadmap.
Week | Phase | Start | End | Step | Task | Status
1 | Setup and bench test | 2026-10-19 | 2026-10-25 | 1 | Call Dr. B. Balaji Naik to ask about demo/exhibition space and whether a live demo or poster fits | Not started
1 | Setup and bench test | 2026-10-19 | 2026-10-25 | 2 | Order 2 ESP32 boards, capacitive soil sensor, 12V pump with solenoid valve, power adapter | Not started
1 | Setup and bench test | 2026-10-19 | 2026-10-25 | 3 | Wire ESP32 to the kit's sensor board and relay on a breadboard | Not started
1 | Setup and bench test | 2026-10-19 | 2026-10-25 | 4 | Upload a sketch that prints moisture and clicks the relay on/off | Not started
1 | Setup and bench test | 2026-10-19 | 2026-10-25 | 5 | Calibrate sensor: record reading in dry air and in water, map to 0-100% | Not started
2 | Cloud link | 2026-10-26 | 2026-11-01 | 1 | Create Firebase project and Realtime Database | Not started
2 | Cloud link | 2026-10-26 | 2026-11-01 | 2 | Program ESP32 to upload moisture every 10-30 seconds and listen for a 'pump' command | Not started
2 | Cloud link | 2026-10-26 | 2026-11-01 | 3 | Check that changing the pump value in the Firebase console switches the relay | Not started
3 | App core and weather | 2026-11-02 | 2026-11-08 | 1 | Build web app (PWA) with login, live moisture gauge and pump ON/OFF button | Not started
3 | App core and weather | 2026-11-02 | 2026-11-08 | 2 | Add moisture history graph | Not started
3 | App core and weather | 2026-11-02 | 2026-11-08 | 3 | Add Open-Meteo forecast and show rain chance | Not started
3 | App core and weather | 2026-11-02 | 2026-11-08 | 4 | Add auto mode (pump runs if moisture low and rain chance low) with manual override | Not started
3 | App core and weather | 2026-11-02 | 2026-11-08 | 5 | Deploy on Vercel and test from phone on mobile data | Not started
4 | Fertilizer calculator and registration | 2026-11-09 | 2026-11-15 | 1 | Collect recommended doses for 4-5 crops (e.g. sesame, maize, cotton, paddy) from PJTAU/ICAR package of practices | Not started
4 | Fertilizer calculator and registration | 2026-11-09 | 2026-11-15 | 2 | Build calculator: crop + area + optional soil test values gives dose and quantity of urea, DAP, MOP | Not started
4 | Fertilizer calculator and registration | 2026-11-09 | 2026-11-15 | 3 | Add note: general recommendation; soil test gives exact doses | Not started
4 | Fertilizer calculator and registration | 2026-11-09 | 2026-11-15 | 4 | Register via the Google form in the circular before 15 Nov 2026 | Not started
5 | Disease diagnosis and mandi prices | 2026-11-16 | 2026-11-22 | 1 | Add photo upload; send image to a vision AI model from a backend function (API key on server only); show likely problem, treatment and 'confirm with extension officer' note | Not started
5 | Disease diagnosis and mandi prices | 2026-11-16 | 2026-11-22 | 2 | Test with 20-30 real leaf photos of crops you know well | Not started
5 | Disease diagnosis and mandi prices | 2026-11-16 | 2026-11-22 | 3 | Fetch Agmarknet data via data.gov.in API for a few Telangana mandis | Not started
5 | Disease diagnosis and mandi prices | 2026-11-16 | 2026-11-22 | 4 | Save a copy of last good prices so the page works if the API fails | Not started
6 | Polish and rehearse | 2026-11-23 | 2026-11-29 | 1 | Add Telugu interface and offline demo mode | Not started
6 | Polish and rehearse | 2026-11-23 | 2026-11-29 | 2 | Set up demo bed or pots with pump, tubing and sealed box | Not started
6 | Polish and rehearse | 2026-11-23 | 2026-11-29 | 3 | Test the whole system continuously for 2-3 days | Not started
6 | Polish and rehearse | 2026-11-23 | 2026-11-29 | 4 | Prepare poster/banner, 3-minute demo script and backup video in case WiFi fails | Not started
Pack | Pack and travel | 2026-11-30 | 2026-12-01 | 1 | Pack spare ESP32, cables, power strip, phone hotspot and printed QR code for the app link | Not started
[5 empty] | Total tasks | 26
[5 empty] | Tasks done | 0
[5 empty] | Progress | 0%
[5 empty] | Days until conference (2-Dec-2026) | 44

## Budget
Budget estimate (Rs., approximate typical Indian online prices; check current rates before ordering)
Blue = estimates entered from the roadmap. Yellow = fill in your actual spend. Existing kit already covers the relay, jumper wires, starter pump and sensor.
Category | Item | Min (Rs.) | Max (Rs.) | Actual (Rs.)
Hardware | 2 ESP32 boards | 700 | 1000
Hardware | 2 capacitive soil sensors | 300 | 500
Hardware | Power adapter and cables | 300 | 500
Hardware | 12V pump + solenoid valve + adapter | 1000 | 2000
Hardware | Pots, soil, drip tubing, connectors | 500 | 1000
Hardware | Waterproof box, breadboard, wires | 400 | 800
Software | Vision AI API credits | 500 | 1500
Software | Mobile data / hotspot | 300 | 600
Software | Domain name (optional) | 0 | 1000
Software | Hosting (Vercel, Firebase free tiers) | 0 | 0
Conference | Conference registration (Students 1,000; others 3,000) | 1000 | 3000
Conference | Poster / banner printing | 500 | 1500
Conference | Travel, stay and food for 3 days | 3000 | 10000
Subtotals
Hardware | Hardware subtotal | 3200 | 5800 | 0
Software | Software subtotal | 800 | 3100 | 0
Conference | Conference subtotal | 4500 | 14500 | 0
TOTAL |  | 8500 | 23400 | 0
Cushion for replacement parts / second sensor |  | 10% | Assumption: 10% cushion on the max total (from the roadmap advice)
Max total with cushion |  |  | 25740
Budget to keep ready (rounded to nearest Rs. 500) |  |  | 25500 | Roadmap suggested about Rs. 25,000
Lean budget (skip domain, cut travel costs) |  |  | Rs. 12,000-15,000 (from roadmap advice)
Remaining vs. max total (after actual spend) |  |  | 23400
Optional: solar setup (not included in totals)
Category | Item | Min (Rs.) | Max (Rs.) | Actual (Rs.)
Optional | 10W panel + charge controller + 12V battery | 2500 | 4000
Worth it only for a standalone field-style unit; a power socket is enough for a hall demo.

## Demo Day Kit
Pack list (30 Nov - 1 Dec) - tick when packed
Item | Packed?
Spare ESP32 | No
Cables and adapters | No
Power strip | No
Phone hotspot / mobile data | No
Printed QR code for the app link | No
Demo bed or pots with pump, tubing and sealed box | No
Poster / banner | No
3-minute demo script | No
Backup video (in case WiFi fails) | No
Items packed | 0 / 9